## Structural Risk Assessment
RISK ASSESSMENT TEMPLATE
STRUCTURAL RISK ASSESSMENT TEMPLATE
RATING: L - LOW; M - MEDIUM; H - HIGH; NA- NOT APPLICABLE
1 | Amount of time since last major change to existing area of business |  | M |  |  | Ratings |  | RATING * WEIGHT = SCORE
|  | More than 2 years |  |  |  | L=1 | 2*3=6
|  | 1 TO 2 Years |  |  |  | M=2
|  | Less than a year |  |  |  | H=3
|  | No automated system |  |  |  | H=3
2 | Estimated frequency of change to proposed/existing system | No automated system | L |  |  | NA=0 | 1*3=3
|  | Fewer than 2 per year |  |  |  | L=1
|  | 2 to 10 per year |  |  |  | M=2
|  | More than 20 per year |  |  |  | H=3
3 | Estimated extent of total changes in business area methods in last year in percentage of methods affected | No Change | M |  |  | NA=0 | 2*3=6
|  | Less than 10% |  |  |  | L=1
|  | 10 to 25% |  |  |  | M=2
|  | More than 25% |  |  |  | H=3
4 | Critical Staffing of Project | In-House | L |  |  | L=1 | 1*2=2
|  | Contractor - Sole Source |  |  |  | M=2
|  | Contractor - Competitive Bid |  |  |  | H=6
5 | Status of ongoing project training | No training plan required | L |  |  | NA=0 | 1*3=3
|  | Complete training plan in place |  |  |  | L=1
|  | Some training in place |  |  |  | M=2
|  | No training available |  |  |  | H=3 |  |  | s
6 | Level of Skilled Personnel available to train | No training required | L |  |  | NA=0 | 1*3=3
|  | Knowldege on all systems |  |  |  | L=1
|  | Knowldege on major components |  |  |  | M=2
|  | Understanding of few components |  |  |  | H=3
7 | Status of documentation in user area | Complete and current | L |  |  | L=1 | 1*3=3
|  | More than 75% complete and current |  |  |  | M=2
|  | Non existing or outdated |  |  |  | H=6
8 | Availaibility of Test facilities for subsystem testing | Completely available | L |  |  | L=1 | 1*2=2
|  | Underdevelopment |  |  |  | M=2
|  | None available |  |  |  | H=3
Prepared By: |  | Date: |  | Total: | Total Score/Total Weight=Risk Average |  | 28/22=1.27
** The points are specific to projects and can be extended as per the test factors

## Technical Risk Asssessment
RISK ASSESSMENT TEMPLATE
TECHNICAL RISK ASSESSMENT TEMPLATE
RATING: L - LOW; M - MEDIUM; H - HIGH; NA- NOT APPLICABLE
1 | Type of system hardware to be used |  | L |  |  | Ratings | RATING * WEIGHT = SCORE
|  | No hardware needed |  |  |  | NA=0
|  | Standard batch or online system |  |  |  | L=1
|  | Non standard peripherals |  |  |  | M=2
|  | Main frames |  |  |  | H=3
2 | Basis for selection of programing and system software | Architectural analysis of functions and performance | L |  |  | L=1
|  | Similar system development experience |  |  |  | M=2
|  | Existing Programming languages |  |  |  | H=3
3 | Complexity of projected system | Single function | M |  |  | L=1
|  | Multiple but related functions |  |  |  | M=2
|  | Multiple but not related functions |  |  |  | H=3
4 | Level of programming language | High Level | L |  |  | L=1
|  | Low Level |  |  |  | M=2
|  | Special Purpose |  |  |  | H=3
5 | Suitability of programing language with respect to the application | All modules can be coded easily | L |  |  | L=1
|  | All modules can be coded easily with few available functions |  |  |  | M=2
|  | Significant number of existing routines available with sophiticated techniques |  |  |  | H=3
6 | Margin of error | Comfortable margin | L |  |  | L=1
|  | Realistic Margin |  |  |  | M=2
|  | Very Demanding & Unrealistic |  |  |  | H=3
7 | Familiarity of project team with operating system | Considerable experience | L |  |  | L=1
|  | Some experience |  |  |  | M=2
|  | Little or no experience |  |  |  | H=3
8 | Estimated degree of system adaptibililty to change | Structured Programming | L |  |  | L=1
|  | Moderate |  |  |  | M=2
|  | Monoithic design with little or no documentation |  |  |  | H=3
Prepared By: |  | Date: |  | Total: | Total Score/Total Weight=Risk Average
** The points are specific to projects and can be extended as per the test factors

## Size Risk Assesment
RISK ASSESSMENT TEMPLATE
SIZE RISK ASSESSMENT TEMPLATE
RATING: L - LOW; M - MEDIUM; H - HIGH; NA- NOT APPLICABLE
1 | Project Implementation Time |  | L |  |  | Ratings | RATING * WEIGHT = SCORE
|  | 12 months or less |  |  |  | L=1
|  | 13 to 24 months |  |  |  | M=2
|  | More than 24 months |  |  |  | H=3
2 | Estimated project adherence to schedule | Ahead | M |  |  | L=1
|  | On time |  |  |  | M=2
|  | Behind |  |  |  | H=3
3 | Number of output reports | Fewer than 10 | L |  |  | L=1
|  | 10 to 20 |  |  |  | M=2
|  | More than 20 |  |  |  | H=3
4 | Line of Code | Less number of LOC | H |  |  | L=1
|  | Moderate |  |  |  | M=2
|  | High Number of LOC |  |  |  | H=3
5 | Percentage of project resources allocated to testing | Low | M |  |  | L=1
|  | Moderate |  |  |  | M=2
|  | High |  |  |  | H=3
Prepared By: |  | Date: |  | Total: | Total Score/Total Weight=Risk Average
** The points are specific to projects and can be extended as per the test factors

## Risk Score Analysis
RISK ASSESSMENT TEMPLATE
RISK SCORE ANALYSIS
APPLICATION SYSTEM:
Risk Area |  | Score |  | Comparitive Rating with Company Applications |  |  |  | Comments
|  | Total | Average | High | Medium |  | Low
Structure
Technical
Size
Total Risk Score
High Risk Attributes
Risk Area |  | Risk Attributes |  |  |  | Test Concerns
Prepared By: |  |  | Date: |  |  | Total:
** The points are specific to projects and can be extended as per the test factors